## ACTIVITY LOG SHEET
ACTIVITY LOG SHEET
Name |  |  |  | Week
Activity | Type (G/I) | Date | Start Time | End Time | Group | Individual
Total |  |  |  |  | 0 | 0
Note:
• G/I refers to “Group/Individual”
• This log sheet should be filled out on individual, weekly basis.
• The log sheets should then form a solid base for the calculation of time and cost management in the project.
• The individual log sheets should also for a solid evidence for the claim of contribution to the project work.

## ACTIVITY LOG SHEET (sample)
ACTIVITY LOG SHEET
Name | John Doe |  |  |  | Week | 7
Activity |  | Type (G/I) | Date | Start Time | End Time | Group | Individual
Group meeting |  | G | 2016-08-22 | 9:00 | 10:00 | 1
Project management |  | I | 2016-08-22 | 10:00 | 12:00 |  | 2
GUI development |  | I | 2016-08-22 | 13:00 | 17:00 |  | 4
Meeting with supervisor |  | G | 2016-08-23 | 10:00 | 11:00:00 | 1
Documentation |  | I | 2016-08-23 | 11:00:00 | 12:00:00 |  | 1
Database connection |  | I | 2016-08-23 | 13:00:00 | 15:00:00 |  | 3
Total | [5 empty] | 2 | 10

## TASK SUMMARY SHEET
Task Summary Sheet |  | Jesse Hare | Week: | 2
Stage | Task | Estimated Work Remaining at Start of Week | Hours Spent this Week | New Estimate
Proj Design Specifics | Finalise framework choice and libraries needed | 3 | 2 | 0
Project Build | Build front end GUI first iteration | 6 | 6 | 0
Project Build | Write code for search algorithm | 5 | 6 | 0
Project Build | Write code for sorting CSV imported elements based on user input | 5 | 5 | 0
Project Build | Iteration Review | 1 | 1 | 0
Cumulative Total: |  | Total: | 20
Note:
• Stage: refer to different stages in methodologies such as Agile, or, use the level 1 tasks in WBS as the entries if your rely on methodologies like "Waterfall".
• "Stage" and "Task" should match those specified in the WBS in project plan
• This sheet should be filled out in individual, weekly basis.
• The sheets should then form a solid base for the calculation of time and cost management in the project.
• The task summary sheets should also for a solid evidence for the claim of contribution to the project work.
• The input should be reflected by the data in "Task completion" and "Task allocation" part in weekly meeting minutes.
Name:

## ACTIVITY LOG SUMMARY SHEET
Activity Log Summary Sheet for: |  |  | Jesse
Stage | Group Work (total time) | Individual Work (total time)
Project Design and Specifics | 2
Project Build | 18
Project Total Time
Total Time | 20 | 0 | 20
Note:
• Stage: refer to different stages in methodologies such as Agile, or, use the level 1 tasks in WBS as the entries if your rely on methodologies like "Waterfall".
• This sheet should be filled out in individual, whole-project basis. The data entered should be calculated based on weekly "Task Summary Sheet"
• The overall laber cost of the project should be accumunated based on all members' "Activity Summary Sheet"s.
• The sheets should then form a solid base for the calculation of time and cost management in the project.
• The task summary sheets should also for a solid evidence for the claim of contribution to the project work.