## TASK SUMMARY SHEET
Task Summary Sheet |  | Ryan Sharp | Week: | 5
Stage | Task | Estimated Work Remaining at Start of Week | Hours Spent this Week | New Estimate
Project Design and Specifics | Design Screen Layouts | 7 | 7
Project Design and Specifics | Finalise Framework choice for GUI development | 7 | 7
Project Design and Specifics | Idenetify any needed libraries (native and external) | 6 | 6
Cumulative Total: 100 |  | Total: | 20
Note:
• Stage: refer to different stages in methodologies such as Agile, or, use the level 1 tasks in WBS as the entries if your rely on methodologies like "Waterfall".
• "Stage" and "Task" should match those specified in the WBS in project plan
• This sheet should be filled out in individual, weekly basis.
• The sheets should then form a solid base for the calculation of time and cost management in the project.
• The task summary sheets should also for a solid evidence for the claim of contribution to the project work.
• The input should be reflected by the data in "Task completion" and "Task allocation" part in weekly meeting minutes.
Name: