## Sheet1
Overall Project time/cost Summary
Stage | Team Member | Hours | Rate(hourly) | Cost
Project Planning | Jesse Hare | 45 | 34.1 | 1534.5
| Ryan Sharp | 77 | 34.1 | 2625.7
| James Mckeown | 45 | 39.9 | 1795.5
| Rick Dobson | 43 | 35.4 | 1522.2
| Vincent Roberts | 38 | 35.4 | 1345.2
Project Analysis/Requirements Elicitation | Jesse Hare | 30 | 34.1 | 1023
| Ryan Sharp | 37 | 34.1 | 1261.7
| James Mckeown | 26 | 39.9 | 1037.4
| Rick Dobson | 27 | 35.4 | 955.8
| Vincent Roberts | 32 | 35.4 | 1132.8
Project Design | Jesse Hare | 36 | 34.1 | 1227.6
| Ryan Sharp | 36 | 34.1 | 1227.6
| James Mckeown | 39 | 39.9 | 1556.1
| Rick Dobson | 40 | 35.4 | 1416
| Vincent Roberts | 20 | 35.4 | 708
Hours/Cost per Project Stage
Project Build | Jesse Hare | 129 | 34.1 | 4398.9 | Stage | Total Hours | Total Cost
| Ryan Sharp | 90 | 34.1 | 3069 | Project Planning | 248 | 8823.1
| James Mckeown | 130 | 39.9 | 5187 | Project Analysis/Requirements Elicitation | 152 | 5410.7
| Rick Dobson | 130 | 35.4 | 4602 | Project Design | 171 | 6135.3 | Overall Project Cost
| Vincent Roberts | 129 | 35.4 | 4566.6 | Project Build | 608 | 21823.5 | 42192.6